## Sheet1
| From | To | Week
January | 2016-01-04 | 2016-01-10 | 1 | - Collecting the data required to do the research: Entomology (ent), Bryophyte (herb), and Lichen (lichens) - Creating an excel sheet with the fields we know of each specimen (it varies from specimen to specimen) - Based on the “gold parsed” group of specimens, deciding what fields are going to be used for the study - Installing a PyBossa server in acis.ufl.edu - Research about related works: identifying uniqueness, advantages, weaknesses of our research |  | Interesting fields to study: - aocr:verbatimScientificName - dwc:eventDate - dwc:verbatimEventDate | Fields with values in ent, herb, and lichens: aocr:verbatimInstitution aocr:verbatimScientificName dwc:catalogNumber dwc:eventDate dwc:identifiedBy dwc:recordedBy dwc:stateProvince dwc:verbatimEventDate dwc:verbatimLocality | ent aocr:verbatimInstitution aocr:verbatimScientificName dwc:catalogNumber dwc:county dwc:eventDate dwc:identifiedBy dwc:recordedBy dwc:sex dwc:stateProvince dwc:verbatimEventDate dwc:verbatimLocality | herb aocr:verbatimInstitution aocr:verbatimScientificName dwc:catalogNumber dwc:country dwc:datasetName dwc:dateIdentified dwc:eventDate dwc:fieldNotes dwc:identifiedBy dwc:recordedBy dwc:recordNumber dwc:scientificName dwc:stateProvince dwc:verbatimEventDate dwc:verbatimLocality | lichens aocr:verbatimInstitution aocr:verbatimScientificName dwc:catalogNumber dwc:country dwc:county dwc:datasetName dwc:decimalLatitude dwc:decimalLongitude dwc:eventDate dwc:habitat dwc:identifiedBy dwc:recordedBy dwc:scientificName dwc:stateProvince dwc:substrate dwc:verbatimCoordinates dwc:verbatimEventDate dwc:verbatimLatitude dwc:verbatimLocality dwc:verbatimLongitude
| 2016-01-11 | 2016-01-17 | 2 | - Create a script to OCR all the images in a specific folder, execute it and get the results for experiment (1) - Define a experiment (2.a) in PyBossa to crop the fields of the Specimens - Upload or link the full images to be cropped in experiment (2.a) - Testing experiment (2.a) in PyBossa, specifically how time is going to be registered - “Crowdsource” for experiment 2.a - Research about related works: identifying uniqueness, advantages, weaknesses of our research
| 2016-01-18 | 2016-01-24 | 3 | - Establish a comparison method of the results from experiment (1) vs. gold results, create a script for it and run it - “Crowdsource” for experiment 2.a - Define a experiment (2.b) in PyBossa to crop the fields (ScientificName and EventDate) of the Specimens, link images, and measure time - “Crowdsource” for experiment 2.b - Research about related works: identifying uniqueness, advantages, weaknesses of our research
| 2016-01-25 | 2016-01-31 | 4 | - Generate statistics and graphs for the experiment (1) vs. gold results comparison - Create a consensus scripts for the cropped images - “Crowdsource” for experiment (2.a) - “Crowdsource” for experiment (2.b)
February | 2016-02-01 | 2016-02-07 | 5 | - “Crowdsource” for experiment (2.a) - “Crowdsource” for experiment (2.b)
| 2016-02-08 | 2016-02-14 | 6 | - “Crowdsource” for experiment (2.a) - For experiment (2.a) Run the consensus script - For experiment (2.a) Run the OCR process for the winner image - Run the comparison script and generate statistics and graphs for the comparison of experiment (2.a) vs. gold results - “Crowdsource” for experiment (2.b)
| 2016-02-15 | 2016-02-21 | 7 | - “Crowdsource” for experiment (2.b) - For experiment (2.b) Run the consensus script - For experiment (2.b) Run the OCR process for the winner image - Adapt or create a new comparison script to compare experiment (2.b) results with the Scientific names and Event dates gotten in the gold process - Run the comparison script and generate statistics and graphs for the comparison of experiment (2.b) vs. gold results
| 2016-02-22 | 2016-02-28 | 8 | - Analyzing results for experiment (1), (2.a), and (2.b). Identify strenghts and weaknesses: execution time, resources needed and time to setup, quality of the results. - Redo experiments, other experiments, and other analysis
March | 2016-02-29 | 2016-03-06 | 9 | - Redo experiments, other experiments, and other analysis
| 2016-03-07 | 2016-03-13 | 10 | - Redo experiments, other experiments, and other analysis
| 2016-03-14 | 2016-03-20 | 11 | - Redo experiments, other experiments, and other analysis
| 2016-03-21 | 2016-03-27 | 12 | - Redo experiments, other experiments, and other analysis | Image padding benefits for OCR
| 2016-03-28 | 2016-04-03 | 13 | - Redo experiments, other experiments, and other analysis | Automatic cleaning, fixing, or reviewing processes could also improve the final result
April | 2016-04-04 | 2016-04-10 | 14 | - Writing paper | Consensus techniques
| 2016-04-11 | 2016-04-17 | 15 | - Writing paper
| 2016-04-18 | 2016-04-24 | 16 | - Writing paper
| 2016-04-25 | 2016-05-01 | 17 | - Writing paper
In Parallel:
- Developing the crowdsourcing and machine-intelligent web platform
Dr. Matsunaga's ideas:
i) can machine detect from 2.a or 2.b when it is doing a bad job, to then send it to crowdsourcing only the pieces it is failing to get?
ii) can machine learn the relative positions of different fields to improve NLP?
[5 empty] | ent | 100
[5 empty] | herb | 100
[5 empty] | lichens | 200

## Sheet2
| Entomology | Bryophyte | Lichens
aocr:regionType
aocr:verbatimInstitution
aocr:verbatimScientificName
dwc:associatedTaxa
dwc:catalogNumber
dwc:country
dwc:county
dwc:datasetName
dwc:dateIdentified
dwc:decimalLatitude
dwc:decimalLongitude
dwc:eventDate
dwc:fieldNotes
dwc:habitat
dwc:identifiedBy
dwc:municipality
dwc:occurrenceRemarks
dwc:recordedBy
dwc:recordNumber
dwc:scientificName
dwc:sex
dwc:stateProvince
dwc:substrate
dwc:verbatimCoordinates
dwc:verbatimElevation
dwc:verbatimEventDate
dwc:verbatimLatitude
dwc:verbatimLocality
dwc:verbatimLongitude